## PMBOK Master
| Body of Knowledge | Processes | Inputs | Tools & Techniques | Outputs
| Integration Management | Plan Development | Other planning outputs | Planning methodology | Plan
|  |  | Historical Info | Stakeholder skills & knowledge | Supporting detail
|  |  | Org policies | PM Information System (PMIS)
Constraints/Assumptions
|  | Plan Execution | Plan | Mgmt skills | Work results
|  |  | Supporting detail | Product skills and knowledge | Change requests
|  |  | Org policies | Work authorization system
|  |  | Corrective action | Status review meetings
PMIS/Org procedures
|  | Overall Change Control | Plan | Change control system | Plan updates
|  |  | Performance reports | Configuration management | Corrective action
|  |  | Change requests | PMIS/Performance measurement | Lessons learned
Additional planning
| Scope Management | Initiation | Product description | Project selection methods | Project charter
|  |  | Strategic plan | Expert judgement | PM identified/assigned
|  |  | Project selection criteria |  | Constraints
|  |  | Historical information |  | Assumptions
|  | Scope Planning | Product description | Product analysis | Scope statement
|  |  | Project charter | Benefit/cost analysis | Supporting detail
|  |  | Constraints/Assumptions | Alternatives identification | Scope management plan
Expert judgement
|  | Scope Definition | Scope statement | WBS templates | WBS
|  |  | Constraints/Assumptions | Decomposition
Other planning outputs
Historical information
|  | Scope Verification | Work results | Inspection | Formal acceptance
Product documentation
|  | Change Control | WBS's | Scope change control system | Scope changes
|  |  | Performance reports | Performance measurement | Corrective Action
|  |  | Change requests | Additional planning | Lessons learned
Scope management plan
| Time Management | Activity Definition | WBS | Decomposition | Activity list
|  |  | Scope statement | Templates | Supporting detail
|  |  | Historical information |  | WBS updates
Initiating Processes |  |  | Constraints/Assumptions
|  | Activity Sequencing | Activity list | Precedence diagramming method | Network diagram
|  |  | Product description | Arrow diagramming method | Activity list updates
|  |  | Mandatory, Discretionary and External dependencies | Conditional diagramming methods
|  |  | Constraints/Assumptions | Network templates
Planning Processes |  | Activity Duration Estimating | Activity List | Expert judgement | Activity duration estimates
|  |  | Constraints/Assumptions | Analogous estimating | Basis of estimates
|  |  | Resource requirements/capabilities | Simulation | Activity list updates
Historical information
|  | Schedule Development | Network diagram | Mathematical analysis | Project schedule
|  |  | Activity duration estimates | Duration compression | Supporting detail
Executing Processes |  |  | Resource requirements | Simulation | Schedule management plan
|  |  | Resource pool description | Resource levelling heuristics | Resource requirement updates
|  |  | Calendars/Constraints/Assumptions | PM software
Leads and lags
|  | Schedule Control | Project schedule | Schedule change control system | Schedule updates
|  |  | Performance reports | Performance measurement | Corrective action
Controlling Processes |  |  | Change requests | Additional planning | Lessons learned
|  |  | Schedule management plan | PM software
| Cost Management | Resource Planning | WBS | Expert judgement | Resource requirements
|  |  | Historical information | Alternatives identification
Scope statement
Resource pool description
Closing Processes |  |  | Organizational policies
|  | Cost Estimating | WBS | Analogous estimating | Cost estimates
|  |  | Resource requirements/rates | Parametric modeling | Supporting detail
|  |  | Activity duration estimates | Bottom-up estimating | Cost management plan
|  |  | Historical information | Computerized tools
Chart of accounts
|  | Cost Budgeting | Cost estimates | Cost estimating tools&techniques | Cost baseline
WBS/Project schedule
|  | Cost Control | Cost baseline | Cost change control system | Revised cost estimates
|  |  | Performance reports | Performance measurement | Corrective action
|  |  | Change requests | Additional planning | Estimate at completion
|  |  | Cost management plan | Computerized tools | Lessons learned
| Quality Management | Quality Planning | Quality policy | Benefit/cost analysis | Quality management plan
|  |  | Scope statement | Benchmarking | Operational definitions
|  |  | Product description | Flowcharting | Checklists
|  |  | Standards and regulations | Design of experiments | Inputs to other processes
Other process inputs
|  | Quality Assurance | Quality management plan | Q planning tolls & techniques | Quality improvement
|  |  | QC measurement results | Quality audits
Operational definitions
|  | Quality Control | Work results | Inspection/Statistical Sampling | Quality improvement
|  |  | Quality management plan | Control charts | Acceptance decisions
|  |  | Operational definitions | Pareto diagrams | Rework
|  |  | Checklists | Flowcharting | Completed checklists
|  |  |  | Trend analysis | Process adjustments
| HR Management | Organizational Planning | Project interfaces | Templates | Role&responsibility assignments
|  |  | Staffing requirements | Human resource practices | Staffing management plan
|  |  | Constraints | Organizational theory | Organizational chart
|  |  |  | Stakeholder analysis | Supporting detail
|  | Staff Acquisition | Staffing management plan | Negotiations | Project staff assigned
|  |  | Staffing pool description | Pre-assignment | Project team directory
|  |  | Recruitment practices | Procurement
|  | Team Development | Project staff/Project plan | Team-building activities | Performance improvements
|  |  | Staffing management plan | General management skills | Input to performance appraisals
|  |  | Performance reports | Reward & recognition systems
|  |  | External feedback | Collocation/Training
| Communications Management | Communications Planning | Comm'cn requirements/technology | Stakeholder analysis | Communications mgmt plan
Constraints/Assumptions
|  | Information Distribution | Work results | Communications skills | Project records
|  |  | Communications mgmt plan | Information retrieval systems
|  |  | Project plan | Information distribution systems
|  | Performance Reporting | Project plan | Performance reviews | Performance reports
|  |  | Work results | Variance analysis/Trend analysis | Change requests
|  |  | Other project records | Earned value analysis
Info distrib'n tools&techniques
|  | Administrative Closure | Perf measurement doc's | Perf reporting tools & techniques | Project archives
|  |  | Project product document |  | Formal acceptance
|  |  | Other project records |  | Lessons learned
| Risk Management | Risk Identification | Product description | Checklists | Sources of risk
|  |  | Other planning outputs | Flowcharting | Potential risk events
|  |  | Historical information | Interviewing | Risk symptoms
Inputs to other processes
|  | Risk Quantification | Stakeholder risk tolerances | Expected monetary value | Opportunities to pursue,
|  |  | Sources of risk | Statistical sums | Threats to respond to
|  |  | Potential risk events | Simulation | Opportunities to ignore,
|  |  | Cost estimates | Decision trees | Threats to accept
|  |  | Activity duration estimates | Expert judgement
|  | Risk Response Development | Opportunities to pursue, | Procurement | Risk management plan
|  |  | threats to respond to | Contingency planning | Inputs to other processes
|  |  | Opportunities to ignore, | Alternative strategies | Contingency plans
|  |  | threats to accept | Insurance | Reserves
Contractual agreements
|  | Risk Response Control | Risk management plan | Workarounds | Corrective action
|  |  | Actual risk events | More risk response development | Updates to risk mgmt plan
Additional risk identification
| Procurement Management | Procurement Planning | Scope statement | Make-or-buy analysis | Procurement mgmt plan
|  |  | Product description | Expert judgment | Statement(s) of work
|  |  | Procurement resources | Contract type selection
Market conditions
Other planning outputs
Constraints/Assumptions
|  | Solicitation Planning | Procurement mgmt plan | Standard forms | Procurement documents
|  |  | Statement(s) of work | Expert judgment | Evaluation criteria
|  |  | Other planning outputs |  | Statement of work updates
|  | Solicitation | Procurement documents | Bidders conferences | Proposals
|  |  | Qualified seller lists | Advertising
|  | Source Selection | Proposals | Contract negotiation | Contract
|  |  | Evaluation criteria | Screening system/Weighting system
|  |  | Organizational policies | Independent estimates
|  | Contract Administration | Contract | Contract change control system | Correspondence
|  |  | Work results | Performance reporting | Contract changes
|  |  | Change requests/Seller invoices | Payment system | Payment requests
|  | Contract Close-out | Contract documentation | Procurement audits | Contract file
Formal acceptance & closure
* WBS = Work Breakdown Structure
Note on B36: Wayne Gilraine P.Eng.:
Project
Management
Body of
Knowledge
Summary
Summarized by:
Delta Cascade
Design Associates Inc.